## SedPod Collection
[11 empty] | Per collection:Dive Budgeted | 400 | Total Budgeted: | 11400
|  |  | Total Spent: | 3920 | [6 empty] | Per collection: Lab Budgeted | 300 | Total Spent | 7020
|  |  | Dive: | 2370 |  | Boat: | 600 |  | Lab: | 950 | Per collection: Boat Budgeted | 200 | Total Surplus | 4380
Dive | Sample | Collection Date | Divers | Total Dive Hours | Boat | Boat driver hours | Total Boat cost | Lab Processing Date(s) | Lab Technician(s) | Lab Tech hours | Notes | Cost per Dive Budgeted | Cost per Dive Actual | Difference
1 | deployed | 2014-03-05 | Meagan Curtis, Tim Clark | 5.5 | Alex SUP | 0 | 0 | N/A |  | 0 | SedPod installation; Tim Clark volunteered, donation in-kind from NPS | 600 | 110 | 490
| 1 | 2014-04-10 | Meagan Curtis, Sean Felise | 17 | Peter's Alia | Flat Rate | 100
2 |  | 2014-04-11 | Meagan Curtis | 3 | Swim | 0 | 0 | 5/13/2014-5/15/14 | Jameson Newtson | 17.5 | Meagan snorkeled reef flat to finish | 900 | 850 | 50
| 2 | 2014-05-17 | Meagan Curtis, Sean Felise | 17 | Peter's Alia | Flat Rate | 100
3 |  | 2014-05-18 | Meagan Curtis | 2 | Swim | 0 | 0 | 6/16/2014-6/17/14 | Jameson Newtson | 10 | Meagan snorkeled reef flat to finish | 900 | 680 | 220
4 | 3 | 2014-06-26 | Meagan Curtis, Sean Felise | 20 | Peter's Alia | Flat Rate | 100 | 7/30/2014-7/31/2014 | Jameson Newtson | 10 |  | 900 | 700 | 200
5 | 4 | 2014-08-14 | Meagan Curtis (Mareike Sudek), Sean Felise | 20 | Peter's Alia | Flat Rate | 100 | 9/6/2014-9/7/2014,9/12/14 | Jameson Newtson | 10 | Mareike filled in for Meagan | 900 | 700 | 200
6 | x | 2014-09-17 | Meagan Curtis, Jameson Newtson | 4 | Hugh Kayak | 0 | 0 | N/A | N/A |  | Kayak flipped and lost SedPods, no collection made | 900 | 80 | 820
7 | 5 | 2014-10-06 | Meagan Curtis, Alex Messina | 10 | Swim | 0 | 0 | 2014-10-08 | Alex Messina | 0 |  | 900 | 200 | 700
8 | 6 | 2014-11-10 | Meagan Curtis, Alex Messina | 10 | Swim | 0 | 0 | 2014-11-12 | Alex Messina |  |  | 900 | 200 | 700
9 | 7 | 2014-12-04 | Meagan Curtis, Alex Messina | 10 | Swim |  | 200 |  | Alex Messina | 0 |  | 900 | 400 | 500
10 | 8 | 2015-01-05 | Jeremy Raynal, Alex Messina | 20 | Swim |  | 0 |  | Alex Messina | 0 |  | 900 | 400 | 500
11 | 9 | 2015-02-01 | Meagan Curtis, Dive Buddy | 20 | Peter's Alia | Flat Rate | 200 |  | Jameson Newtson | 15 |  | 900 | 900 | 0
12 | 10 | 2015-03-01 | Meagan Curtis, Dive Buddy | 20 | Peter's Alia | Flat Rate | 200 |  | Jameson Newtson | 15 |  | 900 | 900 | 0
13 | 11 | 2015-04-01 | Meagan Curtis, Dive Buddy | 20 | Peter's Alia | Flat Rate | 200 |  | Jameson Newtson | 15 |  | 900 | 900 | 0
|  |  | Projected Total | 1200 |  |  | 600 |  |  | 900 | Total: | 11400 | 7020 | 4380

## CRCP Budget
Category | Budgeted | Spent | Remaining | Projected to be Spent | Spent + Projected | Projected to Remain
Dive | 5200 | 2370 | 2830 | 1200 | 3570 | 1630
Lab (ASCC) | 3600 | 950 | 2650 | 900 | 1850 | 1750
DMWR Indirect | 1892 | 0 | 1892 | 0 | 0 | 1892
Boat (Fuel) | 2500 | 600 | 1900 | 800 | 1400 | 1100
Composition Analysis (USD) | 1300 | 127.5 | 1172.5 | 1172.5 | 1300 | 0
Total | 14492 | 4047.5 | 10444.5 | 4072.5 | 8120 | 6372
<-these hours are logged in the Google Doc: https://docs.google.com/spreadsheets/d/1QSObei0llhK4QShhPRag3dJntUOymP44uTE-Dsx4NMs/edit#gid=6